## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a researcher, I want to enter product details, target age, gender and research objective so that I can define a research study. | Must | None | Ruppega G R | Completed
Sprint 1 | Sprint 1 | US-02 | As a researcher, I want to generate AI-powered synthetic personas based on the research inputs so that I can simulate potential users. | Must | US-01 | Ruppega G R | Completed
Sprint 1 | Sprint 1 | US-03 | As a researcher, I want to generate up to 100 synthetic personas so that I can conduct research at a larger scale. | Must | US-02 | Ruppega G R | Completed
Sprint 1 | Sprint 1 | US-04 | As a researcher, I want each generated persona to contain demographic and behavioral attributes so that I can understand different user segments. | Must | US-02 | Ruppega G R | Completed
Sprint 1 | Sprint 1 | US-05 | As a researcher, I want generated personas to be stored so that their information is available across different research modules. | Must | US-02 | Ruppega G R | Completed
Sprint 1 | Sprint 1 | US-06 | As a researcher, I want to view all generated personas in a dashboard so that I can inspect individual users. | Must | US-03 | Ruppega G R | Completed
Sprint 2 | Sprint 2 | US-07 | As a researcher, I want to interview an individual persona so that I can understand its opinions and reasoning. | Must | US-05 | Ruppega G R | Completed
Sprint 2 | Sprint 2 | US-08 | As a researcher, I want interview conversations to maintain memory so that persona responses remain consistent across multiple questions. | Must | US-07 | Ruppega G R | Completed
Sprint 2 | Sprint 2 | US-09 | As a researcher, I want to ask the same question to all personas so that I can compare responses across users. | Should | US-07 | Ruppega G R | Completed
Sprint 2 | Sprint 2 | US-10 | As a researcher, I want to calculate product adoption scores so that I can understand purchase intention across personas. | Must | US-04 | Ruppega G R | Completed
Sprint 2 | Sprint 2 | US-11 | As a researcher, I want to identify recurring themes and sentiment so that I can understand common user opinions. | Must | US-07, US-09 | Ruppega G R | Completed
Sprint 2 | Sprint 2 | US-12 | As a researcher, I want to view aggregated research results so that I can quickly understand persona responses. | Must | US-10, US-11 | Ruppega G R | Completed
Sprint 3 | Sprint 3 | US-13 | As a researcher, I want to ask research questions using natural language so that I can obtain answers from the generated research data. | Should | US-05, US-11 | Ruppega G R | Completed
Sprint 3 | Sprint 3 | US-14 | As a researcher, I want Ask Research responses to be stored so that they can be included in the final research report. | Should | US-13 | Ruppega G R | Completed
Sprint 3 | Sprint 3 | US-15 | As a researcher, I want to validate the system with 100 personas so that I can evaluate its scalability and reliability. | Must | US-03 | Ruppega G R | Completed
Sprint 3 | Sprint 3 | US-16 | As a researcher, I want to generate a downloadable research report so that I can document the research findings. | Should | US-12, US-14 | Ruppega G R | Completed
Sprint 3 | Sprint 3 | US-17 | As a researcher, I want to perform end-to-end testing with 100 personas so that I can identify system failures and inconsistencies. | Must | US-15 | Ruppega G R | Completed
Sprint 3 | Sprint 3 | US-18 | As a researcher, I want research insights to remain consistent across different experiment scenarios so that I can validate insight quality. | Must | US-11, US-17 | Ruppega G R | Completed
Sprint 3 | Sprint 3 | US-19 | As a researcher, I want to document the system architecture and workflow so that the project can be maintained and explained. | Should | All major features | Ruppega G R | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 193 | 13 | 17 | 16 | 18 | 11 | 11 | 12 | 10 | 13 | 13 | 12 | 11 | 17 | 19
SPRINT 1 BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-01 | T01 | Create research setup form | 2026-07-28 | 2026-07-28 | Ruppega G R | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T02 | Add product, description and objective fields | 2026-07-28 | 2026-07-29 | Ruppega G R | Development | Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T03 | Add target age and gender selection | 2026-07-29 | 2026-07-29 | Ruppega G R | Development | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T04 | Implement Gemini persona generation | 2026-07-30 | 2026-07-31 | Ruppega G R | AI Development | Completed | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T05 | Define synthetic persona JSON structure | 2026-07-30 | 2026-07-30 | Ruppega G R | AI Development | Completed | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T06 | Add persona attributes and purchase reasoning | 2026-07-31 | 2026-08-01 | Ruppega G R | AI Development | Completed | 5 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T07 | Implement persona memory storage | 2026-08-01 | 2026-08-03 | Ruppega G R | Backend | Completed | 6 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T08 | Increase persona generation limit from 20 to 100 | 2026-08-04 | 2026-08-05 | Ruppega G R | Backend | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T09 | Implement batch generation for 100 personas | 2026-08-05 | 2026-08-07 | Ruppega G R | Backend | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0
US-03 | T10 | Handle duplicate persona generation | 2026-08-06 | 2026-08-07 | Ruppega G R | Backend | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0
US-06 | T11 | Display generated personas in grid | 2026-08-07 | 2026-08-08 | Ruppega G R | Frontend | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
SPRINT 2 BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-07 | T12 | Create individual persona interview interface | 2026-08-11 | 2026-08-12 | Ruppega G R | Frontend | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T13 | Connect interview UI with Flask API | 2026-08-12 | 2026-08-13 | Ruppega G R | Backend | Completed | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T14 | Store interview conversation history | 2026-08-13 | 2026-08-14 | Ruppega G R | Backend | Completed | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T15 | Maintain persona context across turns | 2026-08-14 | 2026-08-15 | Ruppega G R | AI Development | Completed | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T16 | Implement Ask-All-Personas interview | 2026-08-16 | 2026-08-18 | Ruppega G R | Development | Completed | 7 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T17 | Implement adoption score calculation | 2026-08-18 | 2026-08-19 | Ruppega G R | Analytics | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T18 | Display adoption score per persona | 2026-08-19 | 2026-08-19 | Ruppega G R | Frontend | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
US-11 | T19 | Implement insight extraction | 2026-08-20 | 2026-08-21 | Ruppega G R | AI Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0
US-11 | T20 | Extract themes from responses | 2026-08-21 | 2026-08-22 | Ruppega G R | AI Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0
US-11 | T21 | Implement sentiment analysis | 2026-08-22 | 2026-08-22 | Ruppega G R | AI Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
US-12 | T22 | Create research results dashboard | 2026-08-25 | 2026-08-27 | Ruppega G R | Frontend | Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4
SPRINT 3 BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-15 | T23 | Test generation of 100 personas | 2026-09-01 | 2026-09-02 | Ruppega G R | Testing | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T24 | Test batch generation of 20 personas | 2026-09-01 | 2026-09-01 | Ruppega G R | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T25 | Test combining multiple persona batches | 2026-09-02 | 2026-09-02 | Ruppega G R | Testing | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T26 | Handle duplicate persona names | 2026-09-03 | 2026-09-04 | Ruppega G R | Backend | Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T27 | Verify unique persona IDs | 2026-09-04 | 2026-09-04 | Ruppega G R | Testing | Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T28 | Perform end-to-end testing with 100 personas | 2026-09-05 | 2026-09-06 | Ruppega G R | Testing | Completed | 8 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T29 | Test interview functionality with generated personas | 2026-09-07 | 2026-09-08 | Ruppega G R | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T30 | Test Results dashboard with 100 personas | 2026-09-08 | 2026-09-08 | Ruppega G R | Testing | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-18 | T31 | Test insights using different research scenarios | 2026-09-09 | 2026-09-10 | Ruppega G R | Validation | Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0
US-13 | T32 | Implement Ask Research functionality | 2026-09-10 | 2026-09-10 | Ruppega G R | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
US-14 | T33 | Store Ask Research results | 2026-09-11 | 2026-09-11 | Ruppega G R | Backend | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
US-16 | T34 | Generate downloadable PDF research report | 2026-09-12 | 2026-09-12 | Ruppega G R | Development | Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
US-19 | T35 | Prepare technical documentation | 2026-09-14 | 2026-09-15 | Ruppega G R | Documentation | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4
US-17 | T36 | Fix issues identified during 100-persona testing | 2026-09-14 | 2026-09-15 | Ruppega G R | Bug Fixing | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Difficulty finalizing the synthetic persona data structure | Defined a standard JSON structure for every persona
Sprint 1 | Day 2 | Gemini response format was inconsistent | Added JSON cleaning and validation
Sprint 1 | Day 3 | Some generated persona fields were missing | Added validation and fallback handling
Sprint 1 | Day 4 | Persona attributes needed to be consistent across generated profiles | Standardized persona fields and purchase reasoning
Sprint 1 | Day 5 | Persona data needed to persist between modules | Implemented memory storage
Sprint 1 | Day 6 | Frontend and backend integration issues | Tested API requests and corrected data flow
Sprint 1 | Day 7 | Generating a larger number of personas increased processing time | Started implementing batch generation
Sprint 1 | Day 8 | Persona generation was limited to 20 profiles | Modified the backend to support up to 100 personas
Sprint 1 | Day 9 | Duplicate persona profiles appeared during batch generation | Added duplicate detection and handling
Sprint 1 | Day 10 | Managing 100 personas required better data organization | Improved persona storage and data handling
Sprint 1 | Day 11 | Generated personas were difficult to view efficiently | Implemented a grid-based persona display
Sprint 1 | Day 12 | Some UI elements did not update after generation | Fixed frontend state updates
Sprint 1 | Day 13 | API response handling required additional testing | Tested generation API with different inputs
Sprint 1 | Day 14 | Need to verify complete persona generation workflow | Performed end-to-end testing of persona generation
Sprint 2 | Day 1 | Interview interface required a clear interaction flow | Designed and implemented the individual persona interview interface
Sprint 2 | Day 2 | Interview UI was not properly connected to the backend | Connected the interview interface with the Flask API
Sprint 2 | Day 3 | Interview responses were not being retained between interactions | Implemented conversation history storage
Sprint 2 | Day 4 | Persona context was lost during conversations | Maintained persona context across conversation turns
Sprint 2 | Day 5 | Need to interview multiple personas simultaneously | Implemented Ask-All-Personas functionality
Sprint 2 | Day 6 | Responses from multiple personas were difficult to compare | Structured and grouped responses by persona
Sprint 2 | Day 7 | Need to measure persona adoption | Implemented adoption score calculation
Sprint 2 | Day 8 | Adoption scores were difficult to interpret | Added adoption score display for individual personas
Sprint 2 | Day 9 | Large response sets were difficult to analyze | Implemented automated insight extraction
Sprint 2 | Day 10 | Recurring patterns in responses were difficult to identify | Implemented theme extraction
Sprint 2 | Day 11 | Overall response sentiment was difficult to determine | Implemented sentiment analysis
Sprint 2 | Day 12 | Research findings needed clearer visualization | Created the research results dashboard
Sprint 2 | Day 13 | Some dashboard data required better formatting | Improved dashboard data presentation
Sprint 2 | Day 14 | Complete interview and analysis workflow needed validation | Performed end-to-end testing of interview and analysis modules
Sprint 3 | Day 1 | Generating 100 personas required more processing than smaller batches | Started testing 100-persona generation
Sprint 3 | Day 2 | Multiple API calls were required for large persona generation | Implemented and tested batch generation
Sprint 3 | Day 3 | Combining persona batches could create duplicate profiles | Added duplicate detection between batches
Sprint 3 | Day 4 | Persona IDs needed to remain unique across batches | Implemented unique persona ID validation
Sprint 3 | Day 5 | 100-persona generation required scalability testing | Performed end-to-end testing with 100 personas
Sprint 3 | Day 6 | Interview functionality needed to support the larger persona set | Tested interview functionality with generated personas
Sprint 3 | Day 7 | Results dashboard needed to handle 100 personas | Tested and optimized the Results dashboard
Sprint 3 | Day 8 | Insights needed to work across different research scenarios | Tested insight extraction with multiple scenarios
Sprint 3 | Day 9 | Ask Research results needed to persist between sessions | Implemented Ask Research result storage
Sprint 3 | Day 10 | Research questions needed to be processed across personas | Implemented and tested Ask Research functionality
Sprint 3 | Day 11 | Research findings needed a downloadable format | Implemented PDF research report generation
Sprint 3 | Day 12 | Generated reports required consistent formatting | Improved PDF report structure and formatting
Sprint 3 | Day 13 | Testing identified issues in the 100-persona workflow | Fixed bugs identified during end-to-end testing
Sprint 3 | Day 14 | Final system required documentation and validation | Prepared technical documentation and performed final validation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-28 | 2026-08-10 | Ruppega G R | Start testing UI components earlier | Stop making UI changes without testing | Continue frontend collaboration | Added regular UI testing
2 | Sprint 1 | 2026-07-28 | 2026-08-10 | Ruppega G R | Start validating AI responses systematically | Stop relying only on sample responses | Continue prompt experimentation | Added persona response validation
3 | Sprint 1 | 2026-07-28 | 2026-08-10 | Ruppega G R | Start documenting backend changes | Stop delaying documentation | Continue backend testing | Updated backend documentation
4 | Sprint 2 | 2026-08-11 | 2026-08-31 | Ruppega G R | Start testing complete user flows | Stop testing only individual components | Continue dashboard development | Added integration testing
5 | Sprint 2 | 2026-08-11 | 2026-08-31 | Ruppega G R | Start testing interview edge cases | Stop assuming persona responses will always be consistent | Continue AI integration | Improved interview handling
6 | Sprint 3 | 2026-09-01 | 2026-09-15 | Ruppega G R | Start monitoring batch generation failures | Stop treating one failed persona as a complete failure | Continue backend development | Added batch-level error handling
7 | Sprint 3 | 2026-09-01 | 2026-09-15 | Ruppega G R | Start validating report data against research data | Stop manually checking every report section | Continue documentation | Added report validation checklist
8